M.TECH. DEGREE EXAMINATION, December 2013

Branch: Computer Science Engineering

Specialization: Information Systems

Model Question Paper – I

First Semester

- MCSIS 106-4	 SOFTWARE PROJECT MANAGEMENT

(Regular – 2013 Admissions)

Time: Three Hours		       				   Maximum: 100 marks

Answer all questions.

Any data, if required may be suitably assumed and clearly indicated.

- a. Discuss major causes for software project failures			                    (7 marks)

b. What are the skills and competencies required for a project manager?	        (8 marks)

c. What are the typical contents of a project charter?                                               (10 marks)

OR

2.  a. What are the environmental factors that influence project management?                 (7 marks)

b. Describe major phases of project management life cycle.                                         (8 marks)

c. Discuss the advantages and disadvantages of different project organization types.

(10 marks)

3.  a. What are the benefits of using Work Breakdown Structure (WBS)?                        (6 marks)

b. What are the different techniques for project monitoring and control?                     (7 marks)

c. Explain EVA for project tracking. Give definitions and formula for PV, EV, AC, SV, CV, SPI,

CPI, BAC, EAC, ETC.

You have a project to be completed in 12 months and total cost of project is $100,000. Six months have been passed (and schedule says that 50% of work should be completed). Total money spent on the project is $60,000. But, on a closer look you find that only 40% of work is completed so far. What is SV, CV, SPI, CPI and EAC for this project? Is this project on schedule and within budget?					                                (12 marks)

OR

4. a. How to estimate the activity duration using three point estimate method?

When is this method used normally? 						          (6 marks)

b. Differentiate the purpose of using Network Diagrams, Gantt Chart and Tracking Gantt Chart.

(7 marks)

[P.T.O.]

c. Draw a PDM (AON) network diagram for a project activity list given below. Do CPM analysis and identify the critical path of the project. What is the minimum time required for completion of the project?

| Activity | Description | Predecessor | Duration |
| --- | --- | --- | --- |
| A | Product design | (None) | 5 months |
| B | Market research | (None) | 1 |
| C | Production analysis | A | 2 |
| D | Product model | A | 3 |
| E | Sales brochure | A | 2 |
| F | Cost analysis | C | 3 |
| G | Product testing | D | 4 |
| H | Sales training | B, E | 2 |
| I | Pricing | H | 1 |
| J | Project report | F, G, I | 1 |

(12 marks)

5. a. What are software product and process metrics? Give examples.                                 (6 marks)

b. Differentiate between Quality Assurance and Quality Control. Give examples           (7 marks)

c. What are the software development modes in COCOMO? Give formula for effort / schedule

estimation in Basic COCOMO.							         (12 marks)

OR

6. a. What is the measure for programmer productivity? How to measure the programmer

productivity in a software organization?       					           (6 marks)

b. Differentiate between Verification and Validation. Give examples 		           (7 marks)

c. Explain the steps for software estimation using Function Point Analysis         	         (12 marks)

7. a. Explain two tools/techniques for Risk Analysis.  What are the four techniques for Risk Resolution?                                  						         (12 marks)

- What are the values and principles of Agile Software Development? Explain the use of Sprint burn-down chart?							         (13 marks)

OR

8. a. What are the top ten risks in software projects and what are their mitigation steps?  (12 marks)

b. Explain the procedure for change control & version control in a software project.   (13 marks)